## 2024_2025
UGANDA EITI WORK PLAN FY 2024/2025 GOAL: IMPROVING THE GOVERNANCE OF EXTRACTIVE INDUSTRIES IN UGANDA FOR THE BENEFIT OF PRESENT AND FUTURE GENERATIONS
NO. | Activities | Outputs | Outcomes | Resp. party | Timeline | Cost (UGX) | Funding source
OBJECTIVE 1.0: ENHANCE TRANSPARENCY IN THE EXTRACTIVE SECTOR
1.1 | Disseminate the EITI report findings and sensitise the public about the EITI implementation process | EITI report findings disseminated | Improved awareness and participation in EITI, and its implementation in Uganda | MSG Secretariat | Jul 24 - Jun 25 | 323900000
| a) Engage with Members of Parliament to share report findings i.e. the relevant committee of Parliament preferably the Natural Resources Committee. | 1) One meeting held; and 2) Recorderd Minutes. | Enhanced political buy-in, commitment and engagement from Parliament. | UGEITI & NRC of Parliament | Q4 | 87300000 | GOU
| b) Organize a press conference to publicize the EITI report and follow up with dissemination on radio stations, tv talk shows and newspaper articles. | 1) One press conference held; 2) Eight newspaper articles published; and 3) One radio and One TV show held. | Greater public awareness, engagement and debate. | UGEITI & Media houses | Q2 | 79600000 | GOU
| c) Print copies of the EITI Report and Monograph/Summary for distribution to various stakeholders. | 1) 20 copies of the EITI Report printed; and 2) 500 copies of Monograph printed. | Public knowledge enhanced resulting in active citizenry. | UGEITI | Q2 | 25000000 | GOU
| d) Undertake regional outreach engagements to disseminate the EITI report findings. i.e. Hold workshops in six regions of the country | 1) 6 regional workshops held; and 2) Reports prepared and published. | Increased demand accountability in extractive regions leading to responsive and accountable leadership. | UGEITI | Q2-Q4 | 132000000 | GOU
| e) Prepare, print and disseminate fact sheets or briefs on developments in the extractive sector i.e. information to include contract and license allocation procedures etc. | 1) Two fact sheets prepared and published online; and 500 copies of each version printed. | Increased transparency and knowladge sharing. | UGEITI | Q3 | 3000000 | GOU
| f) Hold strategic meetings/workshop with key institutions of Government for high level buy-in and commitment including MEMD, DGSM and OAG etc; | 1) One high level meeting with top management officials; and 2) a follow up workshop with technical officers held. | Informed decision making. | UGEITI, MEMD, DOP, DGSM & OAG | Q3 | 28950000 | GOU
| g) Prepare Quarterly EITI implementation progress reports for MOFPED, MEMD and the general public. i.e. for circulation to MOFPED leadership, Champions, PS/ST, PS MEMD, Ministry Newsletter. | 1) One quarterly progress report prepared for TPD/MOFPED; 2) one quarterly progress brief prepared for MEMD; and 3) one activity report prepared for MOFPED Times Newsletter. | Increased Government awareness. | UGEITI | Q1-Q4 | 8000000 | GOU
| h) Maintain an updated EITI country website. | Website maintained a nd regularly updated. | An informed and engaged public. | UGEITI | Q1-Q4 | 6750000 | GOU
1.2 | Undertake studies to support revenue mobilisation and management | Study reports prepared | Improved transparency, strategic focus and compliance of the EITI implementation process | MSG Secretariat Consultant | Jul 24 - Jun 25 | 660000000
| a) Conduct a study to inform the digitalisation and mainstreaming of EITI | 1) Feasibility study produced; and 2) Prototype of data mainstreaming system developed. | Capability of Government institutions in data management strengthened. Data accessability enhanced. | UGEITI & Consultatnt | Q4 | 240000000 | World Bank
| b) Conduct a study on the economic potential of Uganda's mining sector | 1) Report prepared; and 2) Findings disseminated. | Enhanced public awareness of the mining sector. | UGEITI & Consultant | Q4 | 180000000 | World Bank
| c) Conduct a study on the revenue potential of Uganda's ASM in the gold sector | 1) Report produced; and 2) Findings disseminated. | Enhanced revenue management. | UGEITI & Consultant | Q4 | 180000000 | World Bank
| d) Finalise the review and adoption of the EITI Strategic Plan for 2025/26 - 2029/30 | Strategic Plan prepared and published. | Improved governance of the extractive sector. | UGEITI & Consultant | Q3 | 10000000 | GOU
| e) Develop a Theory of Change for UGEITI | Theory of Change developed. | Informed stakeholders. | UGEITI & Consultant | Q3 | 50000000 | GOU
1.3 | Prepare and publish the fourth UGEITI report covering FY 2022/2023. | Fourth UGEITI report prepared & published | Improved transparency and accountability so as to ensure that extractives are better managed. | MSG IA | Jul 24 - Jun 25 | 519700000
| a) Develop and approve ToRs for the production of the fourth EITI report i.e. with the support of an Independent Administrator | Terms of Reference prepared and circulated. | Enhanced clarity on EITI report scope and content. | UGEITI | Q2 | 13000000 | GOU
| b) Conduct a scoping study of Uganda's extractive sector to support the production of the EITI report i.e. facilitated by the Independent Administrator | 1) Various meetings held with stakeholders; and 2) Scoping report prepared. | Improved knowledge of the sector. | UGEITI & Consultant | Q3 | 200000000 | GOU
| c) Organise workshop to train the relevant companies and government agencies how to complete the data fillings and templates for purposes of reporting payments and receipts in FY 2022/23. | 1) Training workshop held; 2) Templates prepared; and 3) Training report prepared. | Enhanced knowledge of stakeholders. Increased efficiency and productivity. | UGEITI & Consultant | Q4 | 20700000 | GOU
| d) Conduct reconciliation exercise of the collected data to identify and address any discrepancies i.e. with the technical support of an Independent Administrator | 1) Data reconciliation meetings with stakeholders; and 2) Reconciliation report prepared. | Increased accuracy of EITI data. Improved transparency and efficiency of revenue management. | UGEITI & Consultant | Q4 | 200000000 | GOU
| e) Convene MSG meeting to review the draft EITI Report. | 1) MSG meeting held; and 2) Reviewed draft EITI Report | Enhanced collaboration, participation and ownwership amongst stakeholders. | UGEITI & Consultant | Q4 | 13000000 | GOU
| f) Convene MSG meeting to finalise and approve the EITI Report. | 1) MSG meeting held; and 2) Final draft of EITI Report | Enhanced collaboration, participation and ownwership amongst stakeholders. | UGEITI & Consultant | Q4 | 13000000 | GOU
| g) Launch the EITI Report | EITI Report | Greater public awareness, engagement and debate. | UGEITI | Q4 | 60000000 | GOU
OBJECTIVE 2.0: STRENGTHEN REVENUE MANAGEMENT AND ACCOUNTABILITY
2.1 | Monitor and track the progress made in addressing the recommendations of the previous UGEITI report and the Validation report | Report prepared | Improved governance of the extractive sector. | MSG MEMD Industry URA URSB | Jul 24 - Jun 25 | 52000000
| a) Hold meetings with key stakeholders to discuss and address the recommendations of EITI reports i.e. meetings with CSOs, Industry players and Government. | 1) Meetings held; and 2) Minutes prepared. | Improved governance of the extractive sector. | UGEITI, Industry, CSOs & Relevant MDAs | Q1-Q4 | 30000000 | GOU
| b) Organize one on one follow-up meetings with each concerned institution in order to address recommendations i.e. These should include among others DGSM, PAU, DOP and URA. | 1) Meetings held; and 2) Minutes Prepared. | Improved governance of the extractive sector. | UGEITI, Relevant MDAs | Q1-Q4 | 2000000 | GOU
| c) Organise a workshop with all relevant stakeholders to take stock of the progress on recommendations from the EITI Report and Validation Report | 1) Workshop held; and 2) Report prepared. | Improved governance of the extractive sector. | UGEITI & various stakeholders | Q4 | 20000000 | GOU
OBJECTIVE 3.0: BUILD THE OPERATIONAL AND TECHNICAL CAPACITY OF THE MSG AND SECRETARIAT
3.1 | UGEITI engagements to support EITI implementation | Reports prepared | Increased stakeholder engagementand effective EITI implementation | MSG Secretariat | Jul 24 - Jun 25 | 387000000
| a) Convene meetings for MSG members to the review progress in implementing the workplan. | 1) Eight MSG meetings held; and 2) Meeting minutes prepared. | Improved collaboration, participation and ownwership amongst stakeholders. | UGEITI | Q1-Q4 | 104000000 | GOU
| b) Review the Terms of Reference and membership status of the MSG. | 1) MSG workshop organised: and 2) Terms of Reference reviewed. | Improved collaboration, participation and ownwership amongst stakeholders. | UGEITI | Q3 | 13000000 | GOU
| c) Convene a retreat for MSG members to review the Annual Progress Performance and finalise Annual Progress Report (APR). | 1) MSG Retreat convened; and 2) Report prepared. | Improved collaboration, participation and ownwership amongst stakeholders. | UGEITI | Q3 | 120000000 | GOU
| d) Participate in EITI related conferences, international board meetings, regional meetings and other global engagements. | 1) Conferences attended; and 2) Reports prepared. | Enhanced peer learning and knowledge sharing. | UGEITI | Q1-Q4 | 150000000 | GOU
3.2 | Capacity development of MSG | Reports prepared & Stakeholders training conducted | MSG members' and stakeholders' knowledge, understanding and appreciation of delivery issues improved | MSG Secretariat Stakeholders | Jul 24 - Jun 25 | 58000000
| a) Conduct a refresher training for members of the MSG on EITI reporting | 1) Training undertaken; 2) Report prepared | Enhanced knowledge, attitude, skills and mindset change amongst stakeholders. | UGEITI & International Secretariat | Q3 | 15000000 | GOU
| b) Conduct a training on the EITI Standard requirements particularly for technical officers of Government Institutions under the MSG i.e. MEMD, DGSM, URA, PAU, MOFPED and NEMA etc | 1) Training conducted; and 2) Reports prepared. | Enhanced knowledge, attitude, skills and mindset change amongst stakeholders. | UGEITI & International Secretariat | Q3 | 15000000 | GOU
| c) Conduct a training on EITI topical issues in the extractive industries. Training specificallly for industry MSG members and their technical officers to promote compliance and responsiveness. | 1) Training conducted; and 2) Report prepared. | Enhanced knowledge, attitude, skills and mindset change amongst stakeholders. | UGEITI & Consultant | Q3 | 13000000 | GOU
| d) Conduct a training on the current EITI Standard aimed to support implementaion of provisions in the new Standard i.e. OAG, IGG, NFA to support reporting on recoverable costs, anti-corruption measures, energy transition efforts, etc. | 1) Training conducted; and 2) Report prepared. | Enhanced knowledge, attitude, skills and mindset change amongst stakeholders. | UGEITI & Consultant | Q3 | 15000000 | GOU
3.3 | UGEITI Secretariat Operations | Support to MSG provided | Operational efficiency in EITI implementation delivered | Secretariat | Jul 24 - Jun 25 | 2300000000
| a) UGEITI Secretariat Operations - Including secretariat staff salaries and non-wage expenses inlcuding office equipment, stationery, sitting allowances, computers, fuel and transportation costs, internet subscription, zoom and other software tools, research funding and annual subscription fees for EITI membership. | 1) Staff enumerated; and 2) Secretariat activities undertaken; and 3) Membership cleared. | Effective and efficient operations of UGEITI. | UGEITI Secretariat | Q1-Q4 | 2300000000 | GOU
| Grand Total (UGX) |  |  |  |  | 4300600000